## Start Here
OpenBloom ¦ Project Control Center
A practical checklist for building a portfolio-quality financial data product. Update Status as you work; the dashboard calculates completion.
Topic | Guidance
Project goal | Build a reliable financial research app using public SEC company data, Python, SQL, analytics, data quality, and (later) an evidence-grounded LLM.
Build order | Environment → Git repo → SEC data retrieval → inspect data → SQL/database → deterministic metrics → dashboard → quality/lineage → LLM → evaluation → publish.
Minimum viable product | Search/select one US public company; retrieve company facts; calculate revenue and operating-margin trends correctly; display charts; show source and reporting period; include tests and a clear README.
Important scope rule | Do not start with AI, multiple providers, forecasting, autonomous agents, or a Bloomberg clone. Make one end-to-end workflow reliable first.
Coding assistant | Use one assistant (e.g., ChatGPT for planning/review plus one coding assistant in VS Code). Avoid adding tools until you have a concrete need.
LLM/API billing | A ChatGPT subscription does not automatically include API credits. Check provider billing before wiring an LLM into the app. The core data/analytics MVP does not need an LLM API.
SEC access | Read the SEC EDGAR API documentation and current fair-access guidance. Use an identifying User-Agent, sensible request rates, timeouts, retries, and caching.
Data/licensing | Publicly accessible does not mean every reuse or redistribution is unrestricted. Check provider terms and attribution requirements; cite source filings.
Data correctness | SEC company facts can contain multiple units, durations, annual/quarterly contexts, amendments, and nonstandard fiscal years. Do not blindly select the first value.
Security | Never commit .env files, API keys, tokens, private data, or raw sensitive captures. Use .env.example with placeholders.
Definition of done | A stranger can set it up from the README, reproduce the workflow, inspect source provenance, and run the tests.

## Progress Dashboard
OpenBloom ¦ Progress Dashboard
Status is calculated from the task tracker. Use the dropdown in the Task Tracker sheet.
Total tasks | 51
Completed | 0
In progress | 0
Blocked | 0
Not started | 51
Completion % | 0%
How to use
Open Task Tracker → change Status using the dropdown. Add a date and notes as you work. The dashboard updates when Excel recalculates.

## Task Tracker
OpenBloom ¦ Step-by-Step Task Tracker
Change Status via dropdown: Not Started / In Progress / Blocked / Done. Mark Done only when the acceptance check is satisfied.
ID | Phase | Task | Acceptance check / evidence | Priority | Status | Estimated time | Actual date | Notes / blocker
P0.1 | Scope & planning | Write a one-paragraph problem statement | README states target user, decision supported, and MVP boundary. | Must | Not Started | 30 min
P0.2 | Scope & planning | Create GitHub repository | Repository exists; README and .gitignore committed; no secrets committed. | Must | Not Started | 30 min
P0.3 | Scope & planning | Choose one test company | Record company name, CIK, ticker, and why it is a useful test case. | Must | Not Started | 20 min
P0.4 | Scope & planning | Read SEC API and fair-access guidance | Record endpoints used, User-Agent approach, request limits, and source URLs in docs. | Must | Not Started | 45 min
E1.1 | Environment | Install supported Python 3 version | python --version runs; version is recorded in README. | Must | Not Started | 20 min
E1.2 | Environment | Install VS Code | Can open project folder and integrated terminal. | Must | Not Started | 15 min
E1.3 | Environment | Install Git | git --version runs; name/email configured if needed. | Must | Not Started | 15 min
E1.4 | Environment | Create virtual environment | Project-local .venv exists and can be activated. | Must | Not Started | 15 min
E1.5 | Environment | Install initial packages | Streamlit, pandas, plotly, requests, python-dotenv, pytest install successfully. | Must | Not Started | 20 min
E1.6 | Environment | Create requirements.txt | Dependencies are recorded; a fresh environment can install them. | Must | Not Started | 15 min
E1.7 | Environment | Create .gitignore and .env.example | .venv, __pycache__, .env, database files and caches are excluded appropriately; .env.example has placeholders only. | Must | Not Started | 20 min
E1.8 | Environment | Run a minimal Streamlit app | streamlit run app.py opens locally and displays OpenBloom title. | Must | Not Started | 20 min
E1.9 | Environment | Make first Git commit | git status is clean after commit; no credentials or large raw files included. | Must | Not Started | 15 min
D2.1 | SEC ingestion | Read SEC company-facts documentation | Understand company submissions vs company facts and the expected JSON shape. | Must | Not Started | 30 min
D2.2 | SEC ingestion | Implement HTTP client | Timeouts, status checking, helpful errors, identifying User-Agent, and reasonable request pacing are implemented. | Must | Not Started | 60 min
D2.3 | SEC ingestion | Fetch company facts for one CIK | A script saves or returns a real response successfully; retrieval time and source are logged. | Must | Not Started | 45 min
D2.4 | SEC ingestion | Inspect raw response structure | Document concepts, units, forms, fiscal periods, and fields needed; don't assume one tag covers all companies. | Must | Not Started | 45 min
D2.5 | SEC ingestion | Add caching / avoid repeated requests | Repeated runs don't needlessly refetch unchanged data; behavior is documented. | Should | Not Started | 45 min
D2.6 | SEC ingestion | Handle bad CIK, HTTP errors, and malformed JSON | Tests show graceful failure with useful error messages. | Must | Not Started | 45 min
M3.1 | Data modeling & SQL | Design a small data dictionary | Each chosen field has definition, unit, grain, source, and known limitations. | Must | Not Started | 45 min
M3.2 | Data modeling & SQL | Design SQLite schema | Tables/keys preserve company, concept, unit, period, filing/source, and ingestion metadata. | Must | Not Started | 60 min
M3.3 | Data modeling & SQL | Create database tables | Schema is created reproducibly by code or a SQL script. | Must | Not Started | 45 min
M3.4 | Data modeling & SQL | Normalize selected financial facts | Values preserve units, duration/instant context, filing form, fiscal period, and source reference. | Must | Not Started | 90 min
M3.5 | Data modeling & SQL | Load normalized records into SQLite | Can query records after app/script restarts; duplicate handling is defined. | Must | Not Started | 60 min
M3.6 | Data modeling & SQL | Write SQL trend query using LAG | Query returns ordered periods and previous-period value; you can explain the window function. | Must | Not Started | 45 min
M3.7 | Data modeling & SQL | Document annual vs quarterly logic | Metric selection avoids mixing incompatible durations, units, periods, or amended filings without a rule. | Must | Not Started | 60 min
A4.1 | Analytics | Implement revenue growth calculation | Formula is tested; missing prior period and zero denominator are handled explicitly. | Must | Not Started | 45 min
A4.2 | Analytics | Implement operating margin calculation | Operating income / revenue uses compatible periods and units; missing or zero revenue handled. | Must | Not Started | 45 min
A4.3 | Analytics | Validate outputs against source facts | At least two periods are manually checked against source data and calculations independently reproduced. | Must | Not Started | 60 min
A4.4 | Analytics | Create company overview metrics | UI shows company identity, periods available, filing date/source, and data freshness. | Must | Not Started | 45 min
A4.5 | Analytics | Create Plotly charts | Revenue, operating income, and margin trends render with labels, units, and period context. | Must | Not Started | 60 min
Q5.1 | Data quality & lineage | Add missing/duplicate/unit checks | Quality checks run automatically and surface actionable issues. | Must | Not Started | 60 min
Q5.2 | Data quality & lineage | Track ingestion runs and failures | Each run has timestamp, status, source, and error summary. | Should | Not Started | 45 min
Q5.3 | Data quality & lineage | Show metric provenance | A user can inspect the source filing, source concept, period, unit, and calculation behind a metric. | Must | Not Started | 60 min
Q5.4 | Data quality & lineage | Create a data-flow diagram | Diagram documents source → ingestion → raw/normalized data → analytics → UI/LLM. | Should | Not Started | 45 min
Q5.5 | Data quality & lineage | Create a basic risk/issue register | Document data limitations, licensing, stale data, metric ambiguity, and AI hallucination risks with mitigations. | Should | Not Started | 45 min
L6.1 | LLM research | Choose one provider and verify API access | Provider terms/pricing are reviewed; API key is stored outside source control. | Should | Not Started | 30 min
L6.2 | LLM research | Define a small question set | At least 10 questions with expected evidence or a documented 'insufficient evidence' answer. | Should | Not Started | 45 min
L6.3 | LLM research | Retrieve filing evidence before generation | The model receives bounded, relevant excerpts/facts with source IDs, not arbitrary unsupported context. | Should | Not Started | 90 min
L6.4 | LLM research | Implement structured response schema | Response separates summary, observations, evidence references, and limitations; malformed output is handled. | Should | Not Started | 60 min
L6.5 | LLM research | Validate citations and claims | Displayed references exist and support the associated claim; unsupported answers are flagged or rejected. | Must | Not Started | 90 min
L6.6 | LLM research | Record evaluation results | Test set records expected evidence, model output, pass/fail rationale, and failure cases. | Should | Not Started | 60 min
T7.1 | Testing & reliability | Write unit tests for calculations | Tests cover typical values, missing data, zero denominator, negative values where relevant, and rounding. | Must | Not Started | 60 min
T7.2 | Testing & reliability | Write ingestion tests with mocked responses | Tests cover success, HTTP failure, timeout, and malformed payload. | Must | Not Started | 60 min
T7.3 | Testing & reliability | Run full test suite | pytest completes successfully; failures are resolved or documented. | Must | Not Started | 30 min
T7.4 | Testing & reliability | Test clean setup from README | A fresh virtual environment can install dependencies and run the app using documented steps. | Must | Not Started | 45 min
R8.1 | Release & portfolio | Complete README | Problem, features, architecture, setup, data sources, screenshots, testing, limitations, roadmap are documented. | Must | Not Started | 60 min
R8.2 | Release & portfolio | Add screenshots / short demo | Screenshots use legitimate data and show source/period context; no secrets or private info visible. | Should | Not Started | 30 min
R8.3 | Release & portfolio | Review data-source terms and attribution | README clearly explains source attribution, usage constraints, and what is or isn't redistributed. | Must | Not Started | 30 min
R8.4 | Release & portfolio | Publish first usable release | Repository is reproducible; core workflow works; limitations are candidly stated. | Must | Not Started | 45 min
R8.5 | Release & portfolio | Write resume bullets based on shipped features | Each bullet is verifiable and contains no invented impact metrics. | Should | Not Started | 30 min

## PC Prerequisites
OpenBloom ¦ PC Setup & Prerequisites
Install only what you need for the MVP. Keep the setup simple; add tools later only when a task requires them.
Item | Required? | Purpose | Install / verify | Verification | Notes
Windows 10/11 updates | Recommended | Stable, patched development environment | Run Windows Update and restart if required | Windows Update reports no pending required restart | Avoid installing unrelated tools during setup.
Python 3 | Required | Run the app, data pipeline, tests | Install a current stable Python 3 release from python.org; enable launcher/PATH options if offered | py --version and python --version (at least one should work) | Use one Python version consistently; record it in README.
Visual Studio Code | Required/recommended | Edit files and use integrated terminal | Install from official VS Code website | code --version or open the app manually | Python extension is useful.
Git | Required | Version control and GitHub workflow | Install Git for Windows | git --version | Set user.name and user.email if commits ask for them.
GitHub account | Required for public portfolio | Host repository and issue tracker | Create/sign in at GitHub | Can create a repository | Do not publish API keys, private data, or unredacted traces.
Python virtual environment | Required | Isolate project dependencies | python -m venv .venv | Activate it; python -m pip --version points inside .venv | Do not commit .venv.
Python packages | Required | App, data processing, HTTP, tests | pip install streamlit pandas plotly requests python-dotenv pytest | python -m pip show streamlit pandas plotly requests python-dotenv pytest | Use requirements.txt for repeatable installs.
SEC API docs and User-Agent | Required | Access public company facts responsibly | Read SEC EDGAR API docs and fair-access guidance; configure an identifying User-Agent | One successful request and documented source URL | No API key is typically required for SEC company submissions/company facts; obey current policies.
LLM API account/key | Optional for initial MVP | Generate evidence-grounded research summaries | Choose one provider only when ready; review pricing and API terms | A small test request succeeds, if enabled | ChatGPT subscription and API billing are separate.
SQLite | Included with Python | Local relational database | Use Python sqlite3; no separate server needed | Python can import sqlite3 and create a test DB | Do not add PostgreSQL yet unless needed.
Excel / LibreOffice | Optional | Track progress and inspect spreadsheet outputs | Use Excel or LibreOffice Calc | Can open this workbook | Not required to build OpenBloom.
Power BI Desktop | Optional, later | Separate BI portfolio artifact | Install only if you decide to make a Power BI case study | Power BI opens and imports sample data | Not required for OpenBloom MVP.
Docker | Not required initially | Containerization / reproducible deployment later | Skip for MVP | N/A | Add only after local workflow is stable.
Node.js / React | Not required initially | Separate frontend stack | Skip for Streamlit MVP | N/A | Avoid adding frontend complexity.
Vector database | Not required initially | Large-scale semantic retrieval later | Skip initially | N/A | Start with filing metadata and bounded text retrieval.
API secrets handling | Required if using LLM API | Prevent credential leakage | Use .env locally and .gitignore; .env.example contains placeholders only | git status shows .env ignored | Rotate any key accidentally committed.

## Weekly Plan
OpenBloom ¦ Suggested Weekly Plan
Use this as a guide, not a reason to skip validation. If you are learning Python/SQL simultaneously, stretch the schedule.
Week / session | Focus | Deliverable | Exit criteria | Status
Session 1 | Scope + setup | Repo, venv, Streamlit hello-world | App runs locally; first commit is clean | Not Started
Session 2 | SEC API | One-company data retrieval | Real response retrieved with User-Agent and errors handled | Not Started
Session 3 | Data inspection | Notes on concepts, units, periods, forms | Can explain source JSON and chosen facts | Not Started
Session 4 | SQL + SQLite | Schema and repeatable load | Data persists; queries return correct periods | Not Started
Session 5 | Analytics | Growth/margin functions + tests | Manual calculation matches source values | Not Started
Session 6 | Dashboard + provenance | Company overview and charts | Metrics link back to source and period | Not Started
Session 7 | Quality controls | Quality checks + ingestion run log | Known data issues are visible, not hidden | Not Started
Session 8 | LLM (optional MVP extension) | Evidence-grounded Q&A | Small test set reviewed; unsupported claims are caught or disclosed | Not Started
Session 9 | Release | README, screenshots, clean setup test | A new user can reproduce the core workflow | Not Started

## Learning Log
OpenBloom ¦ Learning & Decision Log
Record what you learned, what the AI suggested, what you verified, and why you made a design decision.
Date | Topic / task | What I learned | AI suggestion | How I verified it | Decision / change | Next question